## Dashboard
Cultural Spec — Live Dashboard
Auto-updates from Field Tracker. Don't edit cells with formulas — just change Status / Phase on the Field Tracker tab and these update.
80 |  | 0 |  | 0
TOTAL FIELDS |  | DONE |  | ADVISOR NEEDED
Overall Progress
0% | of 80 fields complete · 0 done · 80 remaining
By Owner
Owner | Total | Done | In Progress | Advisor | % Complete
Hisham | 25 | 0 | 0 | 0 | 0%
Ohoud | 25 | 0 | 0 | 0 | 0%
Nada | 15 | 0 | 0 | 0 | 0%
Kamal | 15 | 0 | 0 | 0 | 0%
By Phase
Phase | Count | % of Total
1 Drafting | 80 | 100%
2 Cross-Review | 0 | 0%
3 Integration | 0 | 0%
4 Advisor | 0 | 0%
5 YAML Conversion | 0 | 0%
By Status
Status | Count | % of Total
Not Started | 80 | 100%
Drafting | 0 | 0%
Self-Review | 0 | 0%
Cross-Review | 0 | 0%
Integration | 0 | 0%
Advisor Needed | 0 | 0%
Done | 0 | 0%

## Field Tracker
Saudi Cultural Specification — 80-Field Tracker
Lead: Mohammed Rabie · Target ship: 5 weeks from kickoff · Field names are starting points — rename, merge, or split as the team learns
# | Owner | Topic Area | Field Name (suggested — adapt freely) | Status | Phase | Quality Gate | Confidence | Notes / Blockers
1 | Hisham | Wardrobe | Thobe variants by setting (work, majlis, mosque, wedding, beach) | Not Started | 1 Drafting | Pending | experimental
2 | Hisham | Wardrobe | Abaya conventions by brand tier and setting | Not Started | 1 Drafting | Pending | experimental
3 | Hisham | Wardrobe | Bisht rules — when worn, how draped, who wears it | Not Started | 1 Drafting | Pending | experimental
4 | Hisham | Wardrobe | Ghutra and shemagh styling (red vs white, occasions) | Not Started | 1 Drafting | Pending | experimental
5 | Hisham | Wardrobe | Footwear conventions and forbidden styles | Not Started | 1 Drafting | Pending | experimental
6 | Hisham | Wardrobe | Accessories — authentic markers vs. costume markers | Not Started | 1 Drafting | Pending | experimental
7 | Hisham | Wardrobe | Wardrobe restrictions by occasion (Ramadan, Eid, funeral) | Not Started | 1 Drafting | Pending | experimental
8 | Hisham | Gestures | Right-hand rules (serving food, handing items, eating) | Not Started | 1 Drafting | Pending | experimental
9 | Hisham | Gestures | Forbidden gestures and what they signal | Not Started | 1 Drafting | Pending | experimental
10 | Hisham | Gestures | Eye contact norms in mixed-gender settings | Not Started | 1 Drafting | Pending | experimental
11 | Hisham | Gestures | Hand positions in formal photos | Not Started | 1 Drafting | Pending | experimental
12 | Hisham | Gestures | Body posture conventions (sitting, standing, walking) | Not Started | 1 Drafting | Pending | experimental
13 | Hisham | Architecture | Real Saudi home interior vs. Hollywood Middle Eastern | Not Started | 1 Drafting | Pending | experimental
14 | Hisham | Architecture | Majlis configurations and seating conventions | Not Started | 1 Drafting | Pending | experimental
15 | Hisham | Architecture | Kitchen and living room conventions | Not Started | 1 Drafting | Pending | experimental
16 | Hisham | Architecture | Regional differences (Riyadh, Jeddah, Eastern Province) | Not Started | 1 Drafting | Pending | experimental
17 | Hisham | Architecture | Exterior architecture by region | Not Started | 1 Drafting | Pending | experimental
18 | Hisham | Props | Coffee pot rituals (dallah, finjan, serving order) | Not Started | 1 Drafting | Pending | experimental
19 | Hisham | Props | Incense conventions (bukhoor, oud, occasions) | Not Started | 1 Drafting | Pending | experimental
20 | Hisham | Props | Prayer items handling rules | Not Started | 1 Drafting | Pending | experimental
21 | Hisham | Props | Food serving conventions (communal plates, dates) | Not Started | 1 Drafting | Pending | experimental
22 | Hisham | Photography | Angles that work vs. read as foreign | Not Started | 1 Drafting | Pending | experimental
23 | Hisham | Photography | Group photo arrangements | Not Started | 1 Drafting | Pending | experimental
24 | Hisham | Photography | Women framing by brand tier | Not Started | 1 Drafting | Pending | experimental
25 | Hisham | Photography | Men framing conventions | Not Started | 1 Drafting | Pending | experimental
26 | Ohoud | Register | When to use Modern Standard Arabic (MSA) | Not Started | 1 Drafting | Pending | experimental
27 | Ohoud | Register | When to use Najdi dialect | Not Started | 1 Drafting | Pending | experimental
28 | Ohoud | Register | When to use Hejazi dialect | Not Started | 1 Drafting | Pending | experimental
29 | Ohoud | Register | When to mix Arabic and English / when no Arabic | Not Started | 1 Drafting | Pending | experimental
30 | Ohoud | Forbidden | Translated-sounding phrases to avoid | Not Started | 1 Drafting | Pending | experimental
31 | Ohoud | Forbidden | Levantine drift (sounding Lebanese/Syrian when should be Saudi) | Not Started | 1 Drafting | Pending | experimental
32 | Ohoud | Forbidden | English calques to avoid in Arabic copy | Not Started | 1 Drafting | Pending | experimental
33 | Ohoud | Forbidden | Anglicisms that read as inauthentic | Not Started | 1 Drafting | Pending | experimental
34 | Ohoud | Forbidden | Religious-overuse phrases (heavy-handed invocations) | Not Started | 1 Drafting | Pending | experimental
35 | Ohoud | Occasions | Ramadan language by phase (early, middle, last 10) | Not Started | 1 Drafting | Pending | experimental
36 | Ohoud | Occasions | Eid Al-Fitr vs Eid Al-Adha registers | Not Started | 1 Drafting | Pending | experimental
37 | Ohoud | Occasions | National Day vs Founding Day language | Not Started | 1 Drafting | Pending | experimental
38 | Ohoud | Occasions | Condolence and tragedy registers | Not Started | 1 Drafting | Pending | experimental
39 | Ohoud | Occasions | Celebration and milestone registers | Not Started | 1 Drafting | Pending | experimental
40 | Ohoud | Brand voice | Najdi brand voice — when and how | Not Started | 1 Drafting | Pending | experimental
41 | Ohoud | Brand voice | Hejazi brand voice — when and how | Not Started | 1 Drafting | Pending | experimental
42 | Ohoud | Brand voice | Neutral brand voice — when and how | Not Started | 1 Drafting | Pending | experimental
43 | Ohoud | Dialect | Najdi vs Hejazi vocabulary differences | Not Started | 1 Drafting | Pending | experimental
44 | Ohoud | Dialect | Eastern dialect — brand-relevant specifics | Not Started | 1 Drafting | Pending | experimental
45 | Ohoud | Dialect | Southern dialect — brand-relevant specifics | Not Started | 1 Drafting | Pending | experimental
46 | Ohoud | Dialect | Cross-dialect vocabulary with brand implications | Not Started | 1 Drafting | Pending | experimental
47 | Ohoud | Religious | Quranic reference handling with reverence | Not Started | 1 Drafting | Pending | experimental
48 | Ohoud | Religious | Islamic invocation usage (Bismillah, MashaAllah) | Not Started | 1 Drafting | Pending | experimental
49 | Ohoud | Forbidden words | Twitter-drag word list (specific terms to avoid) | Not Started | 1 Drafting | Pending | experimental
50 | Ohoud | Forbidden words | Politically sensitive terms and avoidance | Not Started | 1 Drafting | Pending | experimental
51 | Nada | Egyptian | Egyptian creative tropes Saudi audiences reject | Not Started | 1 Drafting | Pending | experimental
52 | Nada | Levantine | Levantine creative tropes Saudi audiences reject | Not Started | 1 Drafting | Pending | experimental
53 | Nada | Gulf shared | Pan-Gulf conventions vs. specifically Saudi | Not Started | 1 Drafting | Pending | experimental
54 | Nada | Humor | Pan-Arab humor that doesn't land in Saudi | Not Started | 1 Drafting | Pending | experimental
55 | Nada | Gender | Gender representation: Saudi vs. UAE | Not Started | 1 Drafting | Pending | experimental
56 | Nada | Gender | Gender representation: Saudi vs. Egypt | Not Started | 1 Drafting | Pending | experimental
57 | Nada | Gender | Gender representation: Saudi vs. Lebanon | Not Started | 1 Drafting | Pending | experimental
58 | Nada | Audio | Music conventions: Saudi vs. pan-Arab | Not Started | 1 Drafting | Pending | experimental
59 | Nada | Audio | Audio/voiceover register choices | Not Started | 1 Drafting | Pending | experimental
60 | Nada | Western tropes | Imported Western tropes saturated in MENA | Not Started | 1 Drafting | Pending | experimental
61 | Nada | Representation | Romance and intimacy representation across MENA | Not Started | 1 Drafting | Pending | experimental
62 | Nada | Representation | Family representation across MENA | Not Started | 1 Drafting | Pending | experimental
63 | Nada | Representation | Comedy conventions across MENA | Not Started | 1 Drafting | Pending | experimental
64 | Nada | Representation | Authority figure representation | Not Started | 1 Drafting | Pending | experimental
65 | Nada | Representation | Youth and Gen-Z representation | Not Started | 1 Drafting | Pending | experimental
66 | Kamal | Aesthetics | Visual aesthetics: Saudi vs. UAE premium | Not Started | 1 Drafting | Pending | experimental
67 | Kamal | Aesthetics | Visual aesthetics: Saudi vs. Egypt | Not Started | 1 Drafting | Pending | experimental
68 | Kamal | Color | Color associations and connotations in Saudi context | Not Started | 1 Drafting | Pending | experimental
69 | Kamal | Storytelling | Storytelling arc preferences — pacing and beats | Not Started | 1 Drafting | Pending | experimental
70 | Kamal | Reference | Cultural reference layering — sophisticated vs. trying-too-hard | Not Started | 1 Drafting | Pending | experimental
71 | Kamal | Archetypes | 12 archetypes — Saudi calibration overview | Not Started | 1 Drafting | Pending | experimental
72 | Kamal | Archetypes | Hero archetype in Saudi context | Not Started | 1 Drafting | Pending | experimental
73 | Kamal | Archetypes | Sage archetype in Saudi context | Not Started | 1 Drafting | Pending | experimental
74 | Kamal | Archetypes | Lover archetype in Saudi context (sensitive) | Not Started | 1 Drafting | Pending | experimental
75 | Kamal | Archetypes | Outlaw / Rebel archetype in Saudi context (sensitive) | Not Started | 1 Drafting | Pending | experimental
76 | Kamal | Pacing | Resolution vs. ambiguity preferences | Not Started | 1 Drafting | Pending | experimental
77 | Kamal | Pacing | Edit pacing for short-form vs. long-form | Not Started | 1 Drafting | Pending | experimental
78 | Kamal | Premium | Premium markers across MENA | Not Started | 1 Drafting | Pending | experimental
79 | Kamal | Premium | Mid-tier markers across MENA | Not Started | 1 Drafting | Pending | experimental
80 | Kamal | Mistakes | Common Arab agency mistakes in Saudi | Not Started | 1 Drafting | Pending | experimental

## Phase Calendar
5-Week Phase Calendar
Set the kickoff date in B3 and the weekly milestones auto-calculate.
Kickoff date: | 2026-05-19
Week | Phase | Dates | Milestones
Week 1 | 1 Drafting | 19 May – 25 May 2026 | Individual drafting. 6 fields/person/day. Plain prose, not YAML.
Week 2 | 2 Cross-Review | 26 May – 1 Jun 2026 | Each person reads 2 others. Flags contradictions, vagueness, gaps. Rabie collates.
Week 3 | 3 Integration | 2 Jun – 8 Jun 2026 | Half-day session (all 5). Resolve contradictions. Identify advisor-needed fields.
Week 4 | 4 Advisor | 9 Jun – 15 Jun 2026 | Cultural Advisor session. Structured interview on specific fields. Rabie hosts.
Week 5 | 5 YAML Conversion | 16 Jun – 22 Jun 2026 | Rabie converts to YAML. Final read-through. Ship as v1 to repo.

## Advisor Queue
Cultural Advisor Queue
Fields flagged Advisor Needed in the Field Tracker show here. Filter by clicking the header arrows.
# | Owner | Topic | Field Name | Notes / Blockers | Status (for filter)
1 | Hisham | Wardrobe | Thobe variants by setting (work, majlis, mosque, wedding, beach) | 0 | Not Started
2 | Hisham | Wardrobe | Abaya conventions by brand tier and setting | 0 | Not Started
3 | Hisham | Wardrobe | Bisht rules — when worn, how draped, who wears it | 0 | Not Started
4 | Hisham | Wardrobe | Ghutra and shemagh styling (red vs white, occasions) | 0 | Not Started
5 | Hisham | Wardrobe | Footwear conventions and forbidden styles | 0 | Not Started
6 | Hisham | Wardrobe | Accessories — authentic markers vs. costume markers | 0 | Not Started
7 | Hisham | Wardrobe | Wardrobe restrictions by occasion (Ramadan, Eid, funeral) | 0 | Not Started
8 | Hisham | Gestures | Right-hand rules (serving food, handing items, eating) | 0 | Not Started
9 | Hisham | Gestures | Forbidden gestures and what they signal | 0 | Not Started
10 | Hisham | Gestures | Eye contact norms in mixed-gender settings | 0 | Not Started
11 | Hisham | Gestures | Hand positions in formal photos | 0 | Not Started
12 | Hisham | Gestures | Body posture conventions (sitting, standing, walking) | 0 | Not Started
13 | Hisham | Architecture | Real Saudi home interior vs. Hollywood Middle Eastern | 0 | Not Started
14 | Hisham | Architecture | Majlis configurations and seating conventions | 0 | Not Started
15 | Hisham | Architecture | Kitchen and living room conventions | 0 | Not Started
16 | Hisham | Architecture | Regional differences (Riyadh, Jeddah, Eastern Province) | 0 | Not Started
17 | Hisham | Architecture | Exterior architecture by region | 0 | Not Started
18 | Hisham | Props | Coffee pot rituals (dallah, finjan, serving order) | 0 | Not Started
19 | Hisham | Props | Incense conventions (bukhoor, oud, occasions) | 0 | Not Started
20 | Hisham | Props | Prayer items handling rules | 0 | Not Started
21 | Hisham | Props | Food serving conventions (communal plates, dates) | 0 | Not Started
22 | Hisham | Photography | Angles that work vs. read as foreign | 0 | Not Started
23 | Hisham | Photography | Group photo arrangements | 0 | Not Started
24 | Hisham | Photography | Women framing by brand tier | 0 | Not Started
25 | Hisham | Photography | Men framing conventions | 0 | Not Started
26 | Ohoud | Register | When to use Modern Standard Arabic (MSA) | 0 | Not Started
27 | Ohoud | Register | When to use Najdi dialect | 0 | Not Started
28 | Ohoud | Register | When to use Hejazi dialect | 0 | Not Started
29 | Ohoud | Register | When to mix Arabic and English / when no Arabic | 0 | Not Started
30 | Ohoud | Forbidden | Translated-sounding phrases to avoid | 0 | Not Started
31 | Ohoud | Forbidden | Levantine drift (sounding Lebanese/Syrian when should be Saudi) | 0 | Not Started
32 | Ohoud | Forbidden | English calques to avoid in Arabic copy | 0 | Not Started
33 | Ohoud | Forbidden | Anglicisms that read as inauthentic | 0 | Not Started
34 | Ohoud | Forbidden | Religious-overuse phrases (heavy-handed invocations) | 0 | Not Started
35 | Ohoud | Occasions | Ramadan language by phase (early, middle, last 10) | 0 | Not Started
36 | Ohoud | Occasions | Eid Al-Fitr vs Eid Al-Adha registers | 0 | Not Started
37 | Ohoud | Occasions | National Day vs Founding Day language | 0 | Not Started
38 | Ohoud | Occasions | Condolence and tragedy registers | 0 | Not Started
39 | Ohoud | Occasions | Celebration and milestone registers | 0 | Not Started
40 | Ohoud | Brand voice | Najdi brand voice — when and how | 0 | Not Started
41 | Ohoud | Brand voice | Hejazi brand voice — when and how | 0 | Not Started
42 | Ohoud | Brand voice | Neutral brand voice — when and how | 0 | Not Started
43 | Ohoud | Dialect | Najdi vs Hejazi vocabulary differences | 0 | Not Started
44 | Ohoud | Dialect | Eastern dialect — brand-relevant specifics | 0 | Not Started
45 | Ohoud | Dialect | Southern dialect — brand-relevant specifics | 0 | Not Started
46 | Ohoud | Dialect | Cross-dialect vocabulary with brand implications | 0 | Not Started
47 | Ohoud | Religious | Quranic reference handling with reverence | 0 | Not Started
48 | Ohoud | Religious | Islamic invocation usage (Bismillah, MashaAllah) | 0 | Not Started
49 | Ohoud | Forbidden words | Twitter-drag word list (specific terms to avoid) | 0 | Not Started
50 | Ohoud | Forbidden words | Politically sensitive terms and avoidance | 0 | Not Started
51 | Nada | Egyptian | Egyptian creative tropes Saudi audiences reject | 0 | Not Started
52 | Nada | Levantine | Levantine creative tropes Saudi audiences reject | 0 | Not Started
53 | Nada | Gulf shared | Pan-Gulf conventions vs. specifically Saudi | 0 | Not Started
54 | Nada | Humor | Pan-Arab humor that doesn't land in Saudi | 0 | Not Started
55 | Nada | Gender | Gender representation: Saudi vs. UAE | 0 | Not Started
56 | Nada | Gender | Gender representation: Saudi vs. Egypt | 0 | Not Started
57 | Nada | Gender | Gender representation: Saudi vs. Lebanon | 0 | Not Started
58 | Nada | Audio | Music conventions: Saudi vs. pan-Arab | 0 | Not Started
59 | Nada | Audio | Audio/voiceover register choices | 0 | Not Started
60 | Nada | Western tropes | Imported Western tropes saturated in MENA | 0 | Not Started
61 | Nada | Representation | Romance and intimacy representation across MENA | 0 | Not Started
62 | Nada | Representation | Family representation across MENA | 0 | Not Started
63 | Nada | Representation | Comedy conventions across MENA | 0 | Not Started
64 | Nada | Representation | Authority figure representation | 0 | Not Started
65 | Nada | Representation | Youth and Gen-Z representation | 0 | Not Started
66 | Kamal | Aesthetics | Visual aesthetics: Saudi vs. UAE premium | 0 | Not Started
67 | Kamal | Aesthetics | Visual aesthetics: Saudi vs. Egypt | 0 | Not Started
68 | Kamal | Color | Color associations and connotations in Saudi context | 0 | Not Started
69 | Kamal | Storytelling | Storytelling arc preferences — pacing and beats | 0 | Not Started
70 | Kamal | Reference | Cultural reference layering — sophisticated vs. trying-too-hard | 0 | Not Started
71 | Kamal | Archetypes | 12 archetypes — Saudi calibration overview | 0 | Not Started
72 | Kamal | Archetypes | Hero archetype in Saudi context | 0 | Not Started
73 | Kamal | Archetypes | Sage archetype in Saudi context | 0 | Not Started
74 | Kamal | Archetypes | Lover archetype in Saudi context (sensitive) | 0 | Not Started
75 | Kamal | Archetypes | Outlaw / Rebel archetype in Saudi context (sensitive) | 0 | Not Started
76 | Kamal | Pacing | Resolution vs. ambiguity preferences | 0 | Not Started
77 | Kamal | Pacing | Edit pacing for short-form vs. long-form | 0 | Not Started
78 | Kamal | Premium | Premium markers across MENA | 0 | Not Started
79 | Kamal | Premium | Mid-tier markers across MENA | 0 | Not Started
80 | Kamal | Mistakes | Common Arab agency mistakes in Saudi | 0 | Not Started
TIP: Click the arrow in the 'Status (for filter)' header above and select 'Advisor Needed' to see only those rows.

## Quality Bar
Quality Bar — Two Tests Every Field Must Pass
Before marking a field Done, verify it passes both. If either fails, send back for revision.
Test 1 — Specificity
Could this field be written about any Arab country, or is it specifically Saudi?
If it could apply anywhere → not done. Send back. Sharpen with Saudi specifics: place names, brand names, dialect words, occasions, gestures, rules.
Test 2 — Competitor
Could a senior creative at a generic agency write this field by Googling for 30 minutes?
If yes → not deep enough. Add the specific knowledge that you know and Google does not — set knowledge, client war stories, on-the-ground experience, named examples.
Verdict
If a field passes both tests, it ships. Set Quality Gate = Passed Both Tests on the Field Tracker.
Field Format — How to Write Each Entry
FIELD NAME | (one line)
WHAT IT IS | (1–3 sentences plain English)
THE RULE | (the specific rule or convention)
WHY IT MATTERS | (1 sentence about what breaks if this is wrong)
REAL EXAMPLES | (2–3 concrete examples — campaigns, brands, situations)
COMMON MISTAKE | (the specific mistake competitors make on this field)

## Instructions
How to use this tracker
FOR THE TEAM
1. | Go to the Field Tracker tab. Each row is one field. Filter by your own name (Hisham, Ohoud, Nada, Kamal) in the Owner column to see only yours.
2. | Change Status as you progress: Not Started → Drafting → Self-Review → Cross-Review → Done. Each row will color-code itself.
3. | If a field is genuinely outside your expertise, set Status = Advisor Needed. Rabie will queue it for the Cultural Advisor session.
4. | Write your actual content in a separate Google Doc, not in this sheet. This sheet tracks progress. The Doc holds the work.
5. | Use the Notes / Blockers column for anything Rabie should know: contradictions, dependencies, sources you need.
FOR RABIE
· | The Dashboard tab updates live as the team changes statuses. Check it daily during Weeks 1–2.
· | The Phase Calendar tab shows the 5-week timeline. Set the kickoff date in B3 and dates auto-calculate.
· | The Advisor Queue tab lists fields that need outside expertise — filter the Status column to 'Advisor Needed' to see only those rows. Use this list to brief the Cultural Advisor in Week 4.
· | The Quality Bar tab is the two-test checklist. Verify every field passes both before marking Done.
· | Field names in column D are STARTING POINTS. Encourage the team to rename, merge, or split as they learn what the spec actually needs.
THE HARD RULE
⚠ | No AI use for drafting fields. See the Project Brief. The only allowed AI use is Arabic spell-check after writing.
⚠ | If a field is filled in by AI, the moat collapses silently. Read the brief. Hold the line.
STATUS LEGEND
Not Started | Field hasn't been touched yet.
Drafting | Owner is actively writing the first draft.
Self-Review | Owner is reviewing their own draft before sharing.
Cross-Review | Two other team members are reading and flagging.
Integration | Came up in the integration session — being resolved.
Advisor Needed | Team can't confidently fill this — Cultural Advisor required.
Done | Passed both Quality Bar tests. Ready for YAML conversion.